## Sheet1
ID | Description | Probability | Effect | Ranking | Mitigation | How to handle
3 | Someone messed up the code and committed the project | 5 | 9 | 45 |  | 1.Person who messed up the code mysteriously disapears 2.Keep backups
1 | Goup member got sick | 8 | 5 | 40 |  | 1.Split his work between other group members or 2.Motivate the missing group member to work from home
2 | Group member is required to leave country because of personal problems | 4 | 5 | 20 |  | 1.Split his work between other group members 2.Motivate the missing group member to work from home
4 | Equipement fails | 3 | 6 | 18 |  | 1.Ask school for a spare equipement
5 | Requirements change | 7 | 2 | 14 |  | 1.Have meeting and implement the solution
6 | Group member gets a job and decides to leave | 1 | 8 | 8 |  | 1.Have a group meeting and decide on actions to be taken 2.Reorganize the plan of work